## Slide 1: Washington Gas Site
Update September 14, 2017

## Slide 3: Washington Gas Site
WG manufactured gas from coal for lighting and heating from 1888 to the mid-1980s.
Wastes generated include coal tar, purifier box waste, wood chips, ash, cinders, and clinkers. Historical reports show that these wastes were occasionally placed as fill on the site.
The COCs include PAHS, VOCs (particularly benzene), cyanide, naphthalene, and heavy metals.
WG performed voluntary cleanup actions under EPA oversight and currently operates a pump and treat system that is designed to capture contaminated groundwater.

## Slide 4: Washington Gas Site Pre-demolition (1951)
Government Property
Washington Gas (EPA cleanup)
Notes: The MGP buildings, holders, tanks, and other facilities were demolished between 1983 and 1986. MGP-related aboveground oil storage tanks were removed in 1997.

## Slide 5: Washington Gas Site Post demolition (2017)
Government Property
Washington Gas (EPA cleanup)

## Slide 6: Washington Gas Site
September 2012 Consent Decree for “Government Property”
  WG conducting investigation under NPS and DOEE oversight
  NPS is lead agency under CERCLA
Two Operable Units
  OU-1 Soil: Remedial Action completed, re-vegetation monitoring is on-going
  OU-2 Groundwater and impacted river sediments: Investigation is on-going
Notes: Consent Decree for Government Property only: a 4.2-acre parcel located between the WG East Station property and the River
The NPS as lead agency, in partnership with the District, oversees all of Washington Gas’s investigation and cleanup activities as part of a 2012 CD under CERCLA

## Slide 7: Washington Gas Site - OU1
Remedial Action Work Plan approved: excavation of top 3 feet – September 2014
Excavation of contaminated soil completed – July 2015
Revegetation monitoring on-going: Performance standards must be met over two consecutive years
  First seeding event – October 2015
  One year performance evaluation – November 1, 2016
    Performance standards not met
  Modification to seed list approved – March 2017
  Reseeding completed – June and July 2017

## Slide 8: Washington Gas Site – OU2
Activities Completed
  Mobilization 1: soil borings – December 2015
  Mobilization 2: hydraulic profiling – May 2016
  Mobilization 3: well installation and groundwater study – December 2016
  Mobilization 4: hydrographic survey – October 2016
  Mobilization 5: In-river sediment investigation – August 2017
    Manufactured gas impacts observed deeper and over a larger area than anticipated

## Slide 9: Washington Gas Site – OU2 (continued)
To Be Completed
  Mobilization 6: Additional land-side groundwater investigation – September 2017
    Data gap study
  RI Report (draft) – August 2018
  Feasibility Study – 2018
    If Treatability Study needed it may extend completion date to Jan 2020
  Proposed Plan and Record of Decision – 2020