## Sheet1
Anacostia River Sites - Milestone Document and Public Comment Schedule
MILESTONE DOCUMENT | RELEASE DATE1 | PUBLIC COMMENT PERIOD 1,2,3
Anacostia River Sediment Project (ARSP) - Regulatory Authority: DOEE/NPS; Implementer: DOEE (Tetra Tech) and NPS (JCO); doee.dc.gov/anacostiasediment
RTC Matrix for Draft Phase 1 RI | December 2016
Final Phase 1 RI Report | April 2017
Draft Phase 2 RI/FS | November 2017 | November 2017 - January 2018
RTC Matrix for Draft Phase 2 RI/FS | March 2018
Final Phase 2 RI/FS | March 2018
Proposed Plan (PP) | April 2018 | April - May 2018
ROD and RTC Matrix for PP | June 29, 2018
PEPCO - Regulatory Authority: DOEE; Implementer: Pepco (AECOM); www.benningservicecenter.com
Draft RI Report | October 2017 | October - November 2017
Final RI Report | January 2018
Draft FS Report | January 2018 | January - February 2018
Final FS Report | March 2018
Proposed Plan | April 2018 | April - May 2018
Kenilworth Landfill - Regulatory Authority: NPS, Implementer: NPS (JCO); www.nps.gov/nace/learn/management/kplsh.htm
OU-1 Landfill/OU-2 Groundwater
Draft RI Addendum Report | April 2018
Final RI Addendum Report | May 2018
Draft FS Addendum Report | April 2018
Final FS Addendum Report | May 2018
Proposed Plan | June 2018 | June - July 2018
ROD | September 2018
Washington Gas (WG) - Regulatory Authority: NPS; Implementer: WG (AECOM); www.nps.gov/nace/learn/management/wgsite.htm
OU-1 Soil
Remedy Implementation | July 2015
OU-2 Groundwater
Draft RI Report | August 2018
Final RI Report | February 2019
Draft FS Report | February 2019
Final FS Report | July 2020
Proposed Plan | September 2020 | October 2020
ROD | December 2020
Washington Navy Yard (WNY) - Regulatory Authority; EPA Region 3, Implementer: WNY (CH2M)
OU-1 Groundwater
Final RI Report | September 2016
Final FS Report | August 2017
Proposed Plan | March 2018 | March - April 2018
ROD | September 2018
Remedial Design | January 2020
OU-2 Near Shore Sediments
Final FS Report | September 2017
Proposed Plan | April 2018 | April - May 2018
ROD | October 2018
Remedial Design (RD) | January 2020
CSX Transportation - Regulatory Authority: DOEE; Implementer: CSX (Geosyntec Consultants); Documents available upon request at DOEE
Landside Corrective Action | 2015
Post Remediation GW Monitoring | ongoing
Poplar Point - Regulatory Authority: NPS; Implementer: DOEE (Tetra Tech); www.nps.gov/nace/learn/management/poplarpointhistory.htm
Final RI Work Plan | TBD | TBD
RI/FS Report | TBD | TBD
Proposed Plan | TBD | TBD
ROD | TBD | TBD
Southeast Federal Center
Statement of Basis | June 2015
CSOs - Regulatory Authority: EPA Region 3; Implementer: DC Water; www.dcwater.com/content/long-term-control-plan
ART Complete | March 2018
TBD: To be Determined
JCO: The Johnson Company
All documents listed above will be posted on the indicated websites.
The Final Proposed Plan will be incorporated into the ROD at all sites.
1 All dates are best estimates and are subject to change.
2 The public comment period is 30 calendar days unless extended by the regulatory authority.
3 Under CERCLA, a public comment period is required for the Proposed Plan. Some entities will solicit public comments for additional documents.