## Slide 1: Public Comment Period Schedule for Anacostia River Sites
Leadership Council for a
Cleaner Anacostia River
March 9, 2017

## Slide 2: Sites along the Anacostia River
Anacostia River Sediment Project
Kenilworth Landfill
PEPCO
Washington Gas
Washington Navy Yard
CSX Transportation
Poplar Point
Southeast Federal Center
Combined Sewer Overflows (DC Water)

## Slide 3: Sites along the Anacostia River

## Slide 4: Active Site Summary
Kenilworth Landfill – NPS lead. OU-1 Landfill: Supplemental GW Report 2016, additional investigations November 2017– August 2017. Combined ROD
PEPCO Benning Road – DOEE lead. Draft RI 2016, additional sampling January–May 2017
Washington Gas Site – NPS lead. OU-1 Soil: remedial action excavation of top 3 feet in July 2015. OU-2 GW: field investigations December 2015–Spring 2017
Washington Navy Yard Superfund Site – EPA lead. Multiple removal actions at sites and storm sewers 1996-2008. OU-1GW: FS underway. OU-2 Near Shore Sediments: additional sampling March 2016

## Slide 5: Inactive Site Summary
CSX Transportation – DOEE lead. Landside corrective action 2015, GW monitoring ongoing
Poplar Point – NPS lead. All activities leading up to ROD TBD
SE Federal Center – GSA lead. Statement of Basis 2015

## Slide 6: Milestone Documents
SITE | MILESTONE DOCUMENT | RELEASE DATE
ARSP | RTC Matrix for Draft Phase 1 RI | December 2016
 | Final Phase 1 RI Report | April 2017
 | Draft Phase 2 RI/FS | November 2017
 | RTC Matrix for Draft Phase 2 RI/FS | March 2018
 | Final Phase 2 RI/FS | March 2018
 | Proposed Plan (PP) | April 2018
 | ROD and RTC Matrix | June 29, 2018
PEPCO | Draft Final RI Report | October 2017
 | Final RI Report | January 2018
 | Draft FS Report | January 2018
 | Final FS Report | March 2018
 | Proposed Plan | April 2018
KLN | OU-1 Landfill/OU-2 Groundwater | 
 | Draft RI Addendum Report | April 2018
 | Final RI Addendum Report | May 2018
 | Draft FS Addendum Report | April 2018
 | Final FS Addendum Report | May 2018
 | Proposed Plan | June 2018
 | ROD | September 2018

## Slide 7: Milestone Documents
SITE | MILESTONE DOCUMENT | RELEASE DATE
WG | OU-2 Groundwater | 
 | Draft RI Report | August 2018
 | Final RI Report | February 2019
 | Draft FS Report | February 2019
 | Final FS Report | July 2020
 | Proposed Plan | September 2020
 | ROD | December 2020
WNY | OU-1 Groundwater | 
 | Final RI Report | September 2016
 | Final FS Report | August 2017
 | Proposed Plan | March 2018
 | ROD | September 2018
 | Remedial Design (RD) | January 2020
 | OU-2 Near Shore Sediments | 
 | Final FS Report | September 2017
 | Proposed Plan | April 2018
 | ROD | October 2018
PP | Proposed Plan | TBD
 | ROD | TBD

## Slide 8: Public Comment and ROD Schedule
SITE | MILESTONE DOCUMENT | RELEASE DATE | PUBLIC COMMENT PERIOD
ARSP | Draft Phase 2 RI/FS | November 2017 | Nov 2017 - Jan 2018
 | Proposed Plan (PP) | April 2018 | April - May 2018
 | ROD and RTC Matrix | 29-Jun-2018 | 
PEPCO | Draft Final RI Report | October 2017 | October - November 2017
 | Draft FS Report | January 2018 | January - February 2018
 | Proposed Plan | April 2018 | April - May 2018
KL | Proposed Plan | June 2018 | June - July 2018
 | ROD | September 2018 | 
WG OU-2 GW | Proposed Plan | September 2020 | October 2020
 | ROD | December 2020 | 
WNY OU-1 GW | Proposed Plan | March 2018 | March - April 2018
 | ROD | September 2018 | 
WNY OU-2 (SED) | Proposed Plan | April 2018 | April - May 2018
 | ROD | October 2018 | 

## Slide 9: Active Site Document Access
ARSP: doee.dc.gov/anacostiasediment
PEPCO: www.benningservicecenter.com
Kenilworth Landfill: www.nps.gov/nace/learn/management/kplsh.htm
Washington Gas: www.nps.gov/nace/learn/management/wgsite.htm
Washington Navy Yard: SE Library, 403 7th Street SE (on disc)

## Slide 10: Many Sites will Select Remedies in 2018
Anacostia River Sediment Project: ROD June 2018
Kenilworth Landfill: ROD (combined) September 2018
PEPCO: ROD 2018
Washington Navy Yard: OU-1 ROD September 2018, OU-2 ROD October 2018
DC Water CSOs: ART complete March 2018